## Slide 1: Brazil Engineering Hub Solution Summary
Opportunity Name: Legacy Application Modernization PoC — AVA Fabric Agents
Client: ABC Bank
Responsible SA for Brazil Engineering Hub: Rafael S Almeida
Date: 2026-08-21

## Slide 2: Conditions for Brazil Engineering Hub Staffing
Topic | Condition
Resource Availability | This solution summary does not guarantee resource availability. BEH staffing must be confirmed at contract signature; the AVA Fabric Factory pod is a shared service allocated by wave.
Extension Requests | Allocation extensions must be requested with a minimum of 4 weeks' notice. Extending the PoC beyond 4 weeks re-opens the fixed price.
Early termination | If the allocation is terminated early, remaining notice period is charged. Artefacts already produced by executed phases are delivered as-is.
WBS and charging hours | Resources need a WBS level 2 aligned to Avanade Brazil before mobilization. Hours are charged per the BEH Staffing table (800 h total).
AI execution environment | The AI model must run in an environment approved by the bank (dedicated tenant or bank VPC), defined and homologated in Week 1 — the single largest schedule risk.
Source code and IP | The bank grants read access to the legacy repository. Client source code is never used for model training. IP of generated artefacts belongs to the bank; the platform remains Avanade's.
Platform version freeze | The AVA Fabric platform version is frozen for the duration of the PoC. Upgrades are applied only after the executive readout.
Expenses added | Azure infrastructure (~US$ 400 for 4 weeks) and AI model consumption (~US$ 600) are passed through at cost.

## Slide 3: BEH - Solution on a Page
Run the AVA Fabric Agents pipeline end-to-end (F0→F3S) over one legacy banking application selected as pilot.
F0/F1 — AST-based extraction and AS-IS diagnostic: inventory, architecture blueprint, bounded contexts, database analysis, business-rule catalogue, security and gap/risk registers.
F2 — TO-BE architecture: C4 diagrams, ADRs, OpenAPI contracts per bounded context, wave model, migration plan and formal effort estimate (FP/SP/hours).
F3 — Navigable prototype for business validation before any code exists.
F3S — SpecKit: constitution, specifications, plans and an executable, fully traceable backlog.
F4 — Assisted code generation limited to ONE pilot bounded context (.NET 8 + Angular), with a human developer on the build gate.
F5/F6 — Test plan and Terraform IaC for the pilot bounded context only.
F7 — Security & Compliance report (LGPD Arts. 46-50, OWASP, STRIDE, Wave-4 pentest checklist) with CISO and DPO sign-off lines.
Executive readout with adherence report and modernization roadmap recommendation.
Calibrated on a measured end-to-end run of the same pipeline (project nopcommerce-04, Aug 2026)
Fixed 4-week timeline; fixed price; 4 quality gates
One pilot application; one pilot bounded context for codegen
Target stack .NET 8 + Angular (the two GA codegen stacks)
A decision-grade modernization plan for the pilot application, auditable end to end
AS-IS Master Report + business-rule catalogue traceable to source code
TO-BE blueprint, 8 ADRs and OpenAPI contracts per bounded context
Formal effort estimate (FP → SP → hours) defensible at investment committee
Wave model and migration plan with coexistence (Strangler Fig) strategy
Executable backlog with acceptance criteria and dependency graph, consumable by the bank's own squads
Working modular code and Terraform IaC for the pilot bounded context
Security & Compliance report ready for CISO / DPO review
Quantified answer to: what does it cost, how long does it take, and what is the risk
Scope
Estimation Basis
Outcome
Volumetrics
Reference run volumetrics (basis of estimate):
254,001 LOC · 1,731 files · 1,998 classes
15,785 procedures/methods mapped
436 business rules catalogued (of 561 candidates)
10 bounded contexts · 2 god services
8 external APIs · 16 plugins · ~80 tables
394 tasks · 2,991 dependency edges · 15 waves
232 artefacts / 82 MB delivered
F0→F3S in ≈ 2 h 20 min of machine time
Formal estimate: 3,323 h · 892 FP
PoC assumes an application of comparable or smaller size; above 400 KLOC or 15+ BCs requires re-sizing.

## Slide 4: High Level Schedule
Indicative timeline ONLY — 4-week fixed-scope PoC
 | Month 1 |  |  | 
Activity | Week 1 | Week 2 | Week 3 | Week 4
Governance & PMO |  |  |  | 
Mobilization |  |  |  | 
F0-F1 · AS-IS Diagnostic |  |  |  | 
F2 · TO-BE Architecture |  |  |  | 
F3 · Prototype |  |  |  | 
F3S · SpecKit Backlog |  |  |  | 
F4 · Codegen (pilot BC) |  |  |  | 
F5-F6 · QA & IaC |  |  |  | 
F7 · Security & Readout |  |  |  | 
Report & readout
Governance, weekly steering & quality gates
TO-BE architecture, ADRs, OpenAPI
F2 Readiness Gate >=85%
Executive Readout
Specs, plans & executable backlog
Codegen + build gate (pilot BC)
Test plan, IaC & evidence
Navigable prototype
 | Avanade activity
 | ABC Bank activity
 | Quality gate
 | Work Product
 | Deliverable
F3S Exit Gate 100%
Kickoff
Mobilization & AI environment setup
AST extraction + AS-IS diagnostic
F1 Security Gate

## Slide 5: Out of Scope for Brazil Engineering Hub
Mass code generation of the full backlog — F4 is limited to ONE pilot bounded context
Code generation for Java/Spring Boot, Python/FastAPI, Go/Gin or NestJS (not GA in the platform)
Production cutover, go-live or decommissioning of the legacy application
Real data migration, data purge, archiving or sanitization of any kind
Execution of the bank's corporate SAST/DAST scans and penetration testing (the PoC produces the scope, checklist and remediation backlog)
Replacement of the bank's homologation, change-management or release-approval processes
Remediation of vulnerabilities found in the legacy application
Refactoring or maintenance of the legacy code base
Licensing acquisition or procurement (Azure, Microsoft, third-party tooling)
Provisioning or management of production environments
Integration with core banking systems, payment rails or external providers
UAT execution with business users; end-user training, communications or change management
Business process redesign, target operating model or organizational design
Level 1 / Level 2 support, hypercare or post-PoC application support
Formal business sign-off of the business-rule catalogue; any performance or SLA commitment for the generated code; modernization of applications other than the selected pilot
Notes: Files and applications that may stop to work after the migrations should be fixed by Customer | (HyperCare team). (Assumption and Dependency | Risk and mitigate)
After each migration wave any fail will be supported by Hypercare team. Files failed in one wave will be on next waves. (In Scope | Out of Scope)
The migration time is based on a 12GB/h sustained transfer rate that may reduce in accordance with files sizes and Egnyte transfer rate. The effective migration time will be verified by project team during assessment and planning fases. (Assumption and Dependency | Risk mitigate)
Como será o processo de validação de cada onda?

## Slide 6: BEH Staffing
Project Staffing — 4-week PoC |  |  |  |  |  |  |  | 
Team | Role Description | Project Assigned Role | Level | Location | Rate Card | Bill Code | Time Basis | Total Hours
Governance Brazil | PM | Project / Program Manager | Manager | Brazil | Client DO ST | 64 | 10 hrs/week | 40
01 - AVA Fabric | Pipeline / esteira lead | Application Architect | Manager | Brazil | Client DO ST | 64 | 40 hrs/week | 160
01 - AVA Fabric | Platform engineer (runner, gates) | Application Developer | Associate Manager | Brazil | Client DO ST | 58 | 20 hrs/week | 80
02 - AS-IS (F0-F1) | Legacy analyst (.NET / Delphi / VB) | Application Developer | Team Lead / Consultant | Brazil | Client DO ST | 53 | 40 hrs/week | 80
03 - TO-BE (F2-F3S) | TO-BE architect / SpecKit | Application Architect | Team Lead / Consultant | Brazil | Client DO ST | 53 | 40 hrs/week | 80
04 - Codegen (F4) | Senior .NET developer (build gate) | Application Developer | Team Lead / Consultant | Brazil | Client DO ST | 53 | 40 hrs/week | 80
04 - Codegen (F4) | Angular developer | Application Developer | Senior Analyst | Brazil | Client DO ST | 38 | 20 hrs/week | 20
05 - QA (F5) | QA engineer | Test Engineer | Senior Analyst | Brazil | Client DO ST | 38 | 20 hrs/week | 20
06 - DevOps (F6) | DevOps / IaC (Terraform) | Infrastructure Cloud Engineer | Senior Analyst | Brazil | Client DO ST | 38 | 20 hrs/week | 20
07 - Security (F7) | Security & compliance (LGPD / OWASP) | Security Consulting Practitioner | Associate Manager | Brazil | Client DO ST | 58 | 20 hrs/week | 60
AVA Fabric Factory | Pipeline execution — 110 AI agents, 9 phases | AVA Fabric Factory | Shared Service - Onshore | Brazil |  |  | 40 hrs/week | 160
TOTAL | 11 roles · 4 weeks |  |  |  |  |  |  | 800

## Slide 7: Project Organization
ABC Bank
Avanade
Project Manager
Enterprise Architect
CISO / DPO
Executive Sponsor
Codegen Lead (F4-F5)
Business SMEs (rules)
Squad Tech Leads
  Legend
IT Sponsor (ABC Bank)
Executive Sponsor (ABC Bank)
Program Lead (ABC Bank)
Project Manager (ABC Bank)
IT - Infrastructure
AVA Fabric Solution Architect
Esteira Lead (F0-F3S)
Security Lead (F1/F7)
Delivery Lead
PDL
Platform Engineer
Legacy Analyst (AS-IS)
TO-BE Architect
SpecKit Analyst
Senior .NET Developer
Angular Developer
Build Gate Remediation
QA Engineer
Security Architect
LGPD / Privacy SME
OWASP / STRIDE SME
Security Practitioner
Avanade | Brazil
Codegen & Quality
Security & Compliance
AVA Fabric Engine
Code Review
QAD
BEH Delivery Management
AVA Fabric Factory | 110 AI agents · 9 phases (F0-F8) · 6 quality gates
  Delivery Team
  Project Management
  & Technical Oversight
  Program
  Steering Committee
Enterprise Architect (ABC Bank)
DevOps Engineer
IaC (Terraform)
DevOps & IaC
Test Automation
Notes: Slide Purpose: Provides for a representation of Avanade’s understanding of the organisation structure. The project organization chart does not need to include every role to be staffed, just the core roles.
Instructions:
Adjust the organisation chart as appropriate
If ATC is involved, make sure the governance between onshore and offshore are shown
Ensure any Avanade roles represented are aligned with the ‘Estimation Basis’ slide in the main deck

## Slide 8
Solution Scope |  | 
Avanade Scope | Client Scope | Avanade Solution Deliverables / Outcomes
Execute F0/F1 - AST extraction and AS-IS diagnostic of the pilot application Produce the business-rule catalogue with traceability to source code, plus the review pack Execute F2 - TO-BE architecture: C4, ADRs, OpenAPI per BC, wave model, coexistence strategy Produce the formal effort estimate (FP -> SP -> hours, overhead 15%, contingency 20%) Execute F3 and F3S - navigable prototype and executable backlog with acyclic dependency graph Execute F4 - assisted code generation for ONE pilot bounded context, with build-gate remediation Execute F5/F6/F7 - test plan, Terraform IaC and Security & Compliance report for the pilot BC Run the 4 quality gates and deliver the executive readout with roadmap recommendation | Select the pilot application and the pilot bounded context Grant read access to the legacy repository, data dictionary and database schema Approve and homologate the AI model execution environment in Week 1 Provide 1 architect, 1 tech lead and 1 business analyst part-time for validation sessions Provide the Azure subscription used for the pilot DEV environment Validate the business-rule catalogue and the TO-BE architecture at the weekly gates Own change management, homologation, corporate SAST/DAST and any production decision | AS-IS Master Report, inventory, complexity map, risk and gap registers Business-rule catalogue traceable to source + review pack for business validation TO-BE blueprint, 8 ADRs, C4 / ER / sequence diagrams, OpenAPI contracts per BC Effort calculator and AI estimation report (FP / SP / hours) for the full programme Wave model, migration plan, Gantt and coexistence matrix Navigable prototype + executable backlog with acceptance criteria and dependency graph Working modular source code and Terraform IaC for the pilot bounded context Test plan, test cases and functional traceability matrix + Security & Compliance report with CISO / DPO sign-off lines Executive readout: adherence report, measured assertiveness indices and roadmap
Out of Scope -- Key items that are outside the agreed Project Scope
Mass code generation of the full backlog; F4 covers ONE pilot bounded context only Code generation for stacks other than .NET 8 + Angular (Java, Python, Go and NestJS are not GA) Production cutover, go-live, data migration or decommissioning of the legacy application Execution of corporate SAST/DAST and penetration testing; remediation of legacy vulnerabilities Any performance, SLA or capacity commitment for the generated code in production
Solution Blueprint Summary | 
To-Be Solution Summary | Key deviations from Standard solutions of this type/size
Run the AVA Fabric Agents pipeline (110 specialized AI agents, 9 phases F0-F8, 6 blocking quality gates) over one pilot banking application, producing an auditable modernization plan plus a working pilot bounded context on .NET 8 + Angular. | F0-F3S are GA and were executed end-to-end on a 254 KLOC reference code base. F4 (code generation) is Beta: in the reference run all planned files were written, but the build gate failed on first pass (NuGet Central Package Management conflict; Angular CLI missing in the host). Both root causes are configuration/environment level and are remediated before kickoff. F4 is nevertheless scoped as ASSISTED, with a senior developer on the build gate.
AVA Fabric Agents | Solution Scope
Notes: Slide Purpose: Sets the basis of the solution scope of work estimated and what is not included in the solution. Provides a summary of the solution outcomes or what the solution will deliver to the client.
In Scope: Summarize functional & technical scope of the solution to be delivered by Avanade, for example:
  Functional capabilities
  Material Client ownership
  Processes
  Environments
  Technical interfaces
  Key modules
  Third party solutions
  Geographic
  Other options
Out of Scope: Summarize key areas outside of Avanade’s scope of work that might ordinarily be within the scope of the solution delivered, including whether they are covered through Client obligations or are entirely outside of the scope of the Client program
Solution Outcomes: Provide a list of key outcomes that will be delivered when the scope items have been completed be that infrastructure, applications, software, reports, etc. – what will the solution deliver.

## Slide 9: AVA Fabric PoC | Cost & Effort Rationale (Factory Delivery Model)
PoC pricing rationale (4 weeks) - total price = People + Infrastructure + AI model consumption. Every volumetric driver below is measured on a real end-to-end pipeline run (254 KLOC / 394 tasks / 232 artefacts), not estimated by analogy. | 
Cost build-up - what makes the price 1) People - the dominant component 800 billable hours across 11 roles over 4 weeks (see BEH Staffing), priced as SUM(hours x rate card per level); rate cards applied by the commercial team. 640 h named roles (Client DO ST, bill codes 64/58/53/38) + 160 h AVA Fabric Factory pod (Shared Service - Onshore, blended rate). 2) Infrastructure - Azure, 4 weeks, passed through at cost Pipeline runner VM (D8s v5, ~730 h): US$ 280 ¦ DEV environment for the pilot BC: US$ 65 Shared services (ACR + Log Analytics): US$ 45 ¦ Artefact storage and egress: US$ 10 PoC infrastructure total: approx. US$ 400. Full-programme reference: US$ 1,410 / month (DEV + STG + PROD + Shared). 3) AI model consumption - measured, not estimated US$ 1.58 average per codegen task (239,619 input / 45-69k output tokens at US$ 3.00 per M input and US$ 15.00 per M output). F0-F3S (~45 agent executions): US$ 200-400 ¦ F4 on the pilot BC (~40 tasks): US$ 65 ¦ 30% rerun buffer. PoC AI total: approx. US$ 600. Full 394-task migration: approx. US$ 800-1,100. Price formula Price = SUM(hours x rate card) + US$ 400 infrastructure + US$ 600 AI + 15% contingency. Infrastructure and AI together are under 1% of the PoC price - the price is driven by people, not by tokens. | Calculation drivers and measured evidence Legacy code base size (KLOC / files) -> F0-F1, linear. Reference: 254,001 LOC, 1,731 files, 1,998 classes, 15,785 procedures. Domain complexity (# bounded contexts) -> F2-F3S. Reference: 10 BCs, 2 god services, 436 business rules. Backlog volume (# tasks / function points) -> F4, linear per task. Reference: 394 tasks, 2,991 dependency edges, 892 FP, 1,606 SP. Security scope (security flags, SAST/DAST, pentest) -> F1-security and F7. Target stacks (1 backend + 1 frontend vs multiple) -> F4 complexity. Cloud and environments (Azure / AWS / GCP x dev / stg / prd) -> F6 and infrastructure cost. Execution mode (Avanade tenant vs bank VPC / on-premise) -> setup and compliance effort. Measured throughput - basis for the 4-week timeline F0-F1 ~38 min ¦ F2 ~29 min ¦ F3 ~8 min ¦ F3S ~60 min; F0->F3S complete in ~2 h 20 min of machine time. Human time is spent on validation and gate decisions, not on discovery - that is where the 4-week schedule comes from. Value anchor The same pipeline produced a formal estimate of 3,323 h / 892 FP for the full TO-BE implementation. The PoC (800 h) buys the decision-grade plan for that programme plus a working pilot bounded context; traditional discovery of a 254 KLOC application takes 6-10 weeks of squad.
Governance, accountability and commercial conditions Fixed price, gate-controlled: 4 quality gates (F1 Security, F2 Readiness >= 85%, F3S SpecKit Exit 100%, Executive Readout). Gates are blocking, not advisory - the pipeline aborts rather than produce an invalid artefact. No gate, no invoice milestone. Single point of accountability: the AVA Fabric Solution Architect owns plan, governance and sign-offs; the factory pod executes with standardized runbooks, artefact contracts per phase and evidence per task (trace_id, checksums, exit codes, timestamps). AI consumption is measured and immaterial (<1% of price): billing follows delivered value, not model usage. Assumptions: the AI model runs in a bank-approved environment; client source code is never used for model training; IP of generated artefacts belongs to ABC Bank; the platform version is frozen; the bank provides read access to the legacy repository and 1 architect + 1 tech lead + 1 business analyst part-time. Contingency 15% covers one full phase re-run and build-gate remediation on the pilot bounded context - the known Beta risk of F4. Scale-up after the PoC is contracted at fixed price per wave, using the wave model and effort calculator produced by the pipeline itself. | 
Notes: Slide Purpose: Sets the basis of the solution scope of work estimated and what is not included in the solution. Provides a summary of the solution outcomes or what the solution will deliver to the client.
In Scope: Summarize functional & technical scope of the solution to be delivered by Avanade, for example:
  Functional capabilities
  Material Client ownership
  Processes
  Environments
  Technical interfaces
  Key modules
  Third party solutions
  Geographic
  Other options
Out of Scope: Summarize key areas outside of Avanade’s scope of work that might ordinarily be within the scope of the solution delivered, including whether they are covered through Client obligations or are entirely outside of the scope of the Client program
Solution Outcomes: Provide a list of key outcomes that will be delivered when the scope items have been completed be that infrastructure, applications, software, reports, etc. – what will the solution deliver.